## Project Planner
Sydney Airbnb Data
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.0 Planning | 3 | 4 | 3 | 4 | 100%
1.1 Project plan | 3 | 2 | 3 | 2 | 100%
1.2 Scope | 3 | 2 | 3 | 2 | 100%
1.3 WBS | 3 | 2 | 3 | 2 | 100%
1.4 Activity definition | 3 | 4 | 3 | 4 | 100%
1.5 Scheduling and Gantt chart | 3 | 4 | 3 | 4 | 100%
2.0 Software Design Document | 3 | 4 | 3 | 4 | 100%
2.1 System Vision | 3 | 4 | 3 | 4 | 100%
2.2 Formal requirements | 3 | 4 | 3 | 4 | 100%
2.3 Use cases | 3 | 4 | 3 | 4 | 100%
2.4 Software Design / Components | 3 | 4 | 3 | 4 | 100%
2.5 Interface Design | 3 | 4 | 3 | 4 | 100%
3.0 Implementation | 6 | 7 |  |  | 0%
3.1 Test Report | 6 | 7 |  |  | 0%
3.2 Data processing | 5 | 3 |  |  | 0%
3.3 User defined data recall | 7 | 4 |  |  | 0%
3.4 Data visualisation | 7 | 4 |  |  | 0%
3.5 Gui implementation | 9 | 3 |  |  | 0%
4.0 Controlling | 1 | 12
4.1 Progress Meetings | 1 | 12
4.2 Status reports | 1 | 12
4.3 Update plans | 1 | 12
4.4 Update schedual | 1 | 12
4.5 Version control | 1 | 12
5.0 Closing | 10 | 3 |  |  | 0%
5.1 Executive Summary | 10 | 3 |  |  | 0%
5.2 User Manual | 10 | 3 |  |  | 0%
5.3 Self Assessment of Schedule | 12 | 1 |  |  | 0%